## Master Project Schedule
MASTER PROJECT SCHEDULE TEMPLATE
| PROJECT TITLE |  | START DATE
| Plataforma de Videos |  | 2025-02-01 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2025-05-01 |  |  | 90
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2025-02-20 | 2025-02-20 | 1 |  | Not Started
1.1 | – Project Charter | Complete | Gabo | 2025-02-20 | 2025-02-20 | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete | Anette | 2025-02-20 | 2025-02-20 | 1 |  | Complete
1.2 | – Research | Complete | Daniel | 2025-02-20 | 2025-02-20 | 1 |  | On Hold
1.3 | – Projections | Complete | Anette | 2025-02-20 | 2025-02-20 | 1
1.4 | – Stakeholders | Complete | N/A | 2025-02-20 | 2025-02-20 | 1
1.5 | – Guidelines | Complete | Gabo | 2025-02-20 | 2025-02-20 | 1
1.6 | – Project Initiation | Complete | Daniel | 2025-02-20 | 2025-02-20 | 1
2 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting | On Hold |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Communication Plan | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Risk Management | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started |  | 2024-03-03 | 2024-03-26 | 24

## BLANK - Master Project Schedule
MASTER PROJECT SCHEDULE
| PROJECT TITLE |  | START DATE
| Stremeing Video |  | 2025-02-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
|  |  | 2025-05-01 |  |  | 71
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Analisis de Requisitos | Complete |  | 2025-02-20 | 2025-02-26 | 7 |  | Not Started
1.1 | Reuninion Inicial | Complete | Daniel | 2025-02-20 | 2025-02-26 | 7 |  | In Progress
1.2 | Definicion de Requisitos | Complete | Anette | 2025-02-20 | 2025-02-26 | 7 |  | Complete
1.3 | Elaboracion de Documentos | Complete | Gabo | 2025-02-20 | 2025-02-26 | 7 |  | On Hold
2 | Diseño |  |  |  |  | 1
2.1 | Diseño de UI/UX (Mockups) | In Progress | Mata | 2025-02-25 | 2025-03-05 | #REF!
2.2 | Diseño de B.D | In Progress | Gabo | 2025-02-25 | 2025-03-05 | 9
2.3 | Diseño de Backend (endpoints) | In Progress | Anette | 2025-02-25 | 2025-03-05
2.4 | Diseño de Frontend | In Progress | Mata | 2025-02-25 | 2025-03-05
2.5 | Creacion de Diagramas de Caso de Uso | In Progress | TODOS | 2025-02-25 | 2025-03-05
3 | Desarrollo |  |  |  |  | 1
3.1 | Desarrollo de Interfaz de usuario | Not Started | Mata |  |  | 1
3.2 | Desarrollo de navegacion | Not Started | Msts, Anette |  |  | 1
3.2 | Desarrollo Gestion de Uuarios | Not Started | Todos |  |  | 1
3.2.1 | Desarrollo Subida de Videos | Not Started | Gabo |  |  | 1
3.2.2 | Visualizacion y reproduccion de Videos | Not Started | Mata, Anette |  |  | 1
3.2 | Clasifcacion y comentarios | Not Started | Todos |  |  | 1
3.2.1 | Busqueda y filtros | Not Started | Todos |  |  | 1
3.2.2 | Moderacion y Aprobacion de contenido | Not Started | Mata, Anette |  |  | 1
4 | Testing |  |  |  |  | 1
4.1 | Pruebas Unitarias y de integracion |  |  |  |  | 1
4.2 | Pruebas de Carga y de Seguridad |  |  |  |  | 1
4.3 | Ajustes y corecciones de errores |  |  |  |  | 1
5 | Despliegue y Mantenimiento |  |  |  |  | 1
5.1 | Configuracion del Servidor |  | Gabo |  |  | 1
5.2 | Implementacion |  | Todos |  |  | 1
5.3 | Documentacion Final y Planificacion de futuras mejoras |  | Todos |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.